## Sheet1
User Story | Task | Who | Estimate(hrs) | Actual(hrs) | Completed | Replaced By
US1 | Create a database to store property details | Jordan | 2 | 2 | Yes
US1 | Design a user-friendly search interface | Samim | 4 | 4 | Yes
US1 | Implement input validation | Naheed | 2 | 2 | Yes | Samim
US1 | Integrate frontend and backend API | Naheed | 4 | 2 | Yes | Rothchild
US2 | Develop backend code to query the database | Jordan | 5 | 6 | Yes
US2 | Implement notification system for updates | Rothchild | 3 | 3 | Yes
US2 | Design layout for displaying property data | Dmitri | 3 |  | No
US3 | Develop backend code for historical data | Radmir | 4 | 5 | Yes
US3 | Implement filter and sorting options | Radmir | 2 | 1 | Yes
US3 | Design layout for historical data | Samim | 3 | 3 | Yes
US3 | Enable graph for dynamic display | Samim | 2 | 2 | Yes
US4 | Develop backend code to query the database | Radmir | 4 |  | No
US4 | Create a graph for lien data | Dmitri | 3 |  | No
US4 | Add filter and sorting options | Radmir | 2 |  | No
US4 | Enable dynamic graph display | Naheed | 2 |  | No | Jordan
US4 | Notification system for updates | Rothchild | 3 | 1 | Yes
US5 | Notification system for tax status changes | Rothchild | 3 | 1 | Yes
US5 | Retrieve accurate data from the database | Naheed | 4 |  | No | Jordan
US5 | Interface for tax status display | Dmitri | 3 | 2 | Yes