## Iteration 1
User Story | Task | Who | Estimate(hrs) | Actual(hrs) | Completed | Replaced By
US1 | Create a database to store property details | Jordan | 2 | 2 | Yes
US1 | Design a user-friendly search interface | Samim | 4 | 4 | Yes
US1 | Implement input validation | Naheed | 2 | 2 | Yes | Samim
US1 | Integrate frontend and backend API | Naheed | 4 | 2 | Yes | Rothchild
US2 | Develop backend code to query the database | Jordan | 5 | 6 | Yes
US2 | Implement notification system for updates | Rothchild | 3 | 3 | Yes
US2 | Design layout for displaying property data | Dmitri | 3 |  | Yes
US3 | Develop backend code for historical data | Radmir | 4 | 5 | Yes
US3 | Implement filter and sorting options | Radmir | 2 | 1 | Yes
US3 | Design layout for historical data | Samim | 3 | 3 | Yes
US3 | Enable graph for dynamic display | Samim | 2 | 2 | Yes
US4 | Develop backend code to query the database | Radmir | 4 |  | Yes
US4 | Create a graph for lien data | Dmitri | 3 |  | Yes
US4 | Add filter and sorting options | Radmir | 2 |  | Yes
US4 | Enable dynamic graph display | Naheed | 2 |  | Yes | Jordan
US4 | Notification system for updates | Rothchild | 3 | 1 | Yes
US5 | Notification system for tax status changes | Rothchild | 3 | 1 | Yes
US5 | Retrieve accurate data from the database | Naheed | 4 |  | Yes | Jordan
US5 | Interface for tax status display | Dmitri | 3 | 2 | Yes

## Iteration 2
Iteration 2
Task Number | Task Description | Status | Asignees | Actual Hours | Hours Taken for the task
#28 | Story: Users can securely log in to the system using Authentication, ensuring access is restricted to authorized indivuduals based on their roles |  | Dmitri
#30 | Create sign-in form using a modal or login page | Pending | Dmitri
#31 | Create endpoint to handle the post/request of the login form | Pending | Dmitri
#32 | Store account information in the database | Pending | Dmitri
#33 | Create session/cookie containing logged-in user info | Pending | Dmitri
#34 | Switch to 'my account' once login and session is set | Pending | Dmitri
#35 | Story: A broker, investor and agent can generate a report based on client information to provide accurate details |  | Samim
#36 | Design a shared form for brokers, investors, and agents to input client/property information | Pending | Samim
#37 | Develop a POST /api/generate-report endpoint to process the submitted client and property information | Pending | Samim
#38 | Display the report in a downloadable format | Pending | Samim
#39 | Story: Users can securely log in to the system using Authentication, ensuring access is restricted to authorized indivuduals based on their roles | Pending | Rothchild
#40 | Create an alert setup page in settings page in the same place where the user can manage their account | Pending | Rothchild
#41 | Set up the backend API for alert configuration | Pending | Rothchild
#42 | Create a backend job or script to simulate changes | Pending | Rothchild